## Task Details
Task Description | Module | Status | Planned Date | Owner | Comments
Get a new IBM Cloud Account | Environment | Completed
Associate IBM IDs of IBM OMS consultants | Environment | Completed
Request for Baremetal VM to install DB2 and MQ | Environment | Not Applicable
Install Db2 and MQ on VM | Environment | Not Applicable
Connectivity with Kroger (?) This is needed only if we are importing code for Kroger custom build | Environment | Not Applicable
Install Openshift Cluster on IBM Cloud | Openshift | Completed
Install and Configure ICP common Services | Openshift | Completed
Finalize the requirement around Cluster - How many worker nodes | Openshift | Completed |  |  | 5 Worker nodes in the Cluster
Scope for High Availability - Finalize the requirement | Openshift | Not Started
Finalize requirement around self healing and auto scaling - Brian | Openshift | Not Started
Item details including Images | Data Set up | In Progress |  | Reyas | Sample Data received from Kroger
Participant modeling | OMS | Completed |  | Murthy
Node details | Data Set up | Completed |  | Murthy | Sample Data received from Kroger
Inventory Data for the Nodes | Data Set up | Not Started |  | Murthy | Sample Data received from Kroger
Sourcing Rules | Data Set up | In Progress |  | Murthy | Sample Data received from Kroger
Load the OMS OOB images to IBM Cloud registry | OMS | Completed |  | Murthy
Create the prerequisite resources such as Image Stream, Config Map, Secreat etc in Openshift Cluster | OMS | Completed |  | Reyas
Prepare the helm charts for Deployment into Openshift cluster and Complete the deployment | OMS | Completed |  | Reyas
Finalize the requirements for Kroger customization for the MVP and the Demo | OMS | Completed |  | NA | Requirements and use cases are finalized within team and shared with Brian for discussion with Kroger
Configure Integration and agend servers | OMS | Not Started |  | Reyas
Sourcing rules - Configure Sourcing Rules | OMS | In Progress |  | Murthy
Data load for - Items, Nodes, Inventory | OMS | In Progress |  | Murthy
Check new code into Git repository | OMS |  |  | Reyas
Show how the new image is generated | OMS |  |  | Reyas
Show deployment and new image updated in the cluster | OMS |  |  | Reyas
Use Cases: Functional Testing
Manually configure Participant Modeling with One Enterprise, Inventory and Catalog Organizations, and few sample Stores. Manually create Kroger Catalog and Items. | Use Cases
Manually create Inventory for the test items and configure Simple Sourcing Rules. | Use Cases
Create the Orders with Kroger items through REST services (This is to demonstrate that REST service works on Openshift/Container platform) | Use Cases
Asynchronously Create Order with Integration Server (To demonstrate that the integration server works on the platform and can be scaled on demand) | Use Cases
Order Flow in OMS through Agent servers (Release, Schedule, Shipment Creation - Again Kroger uses Agent servers heavily) | Use Cases

## Sheet1
Completed
In Progress
Not Applicable
Not Started